itriX Website Build Execution Plan v0.1

Execution Plan for AI-Powered Website, Compute Bottleneck Review, ALPHA Routing, CRM Capture, and Private MVP Launch

1. Purpose

This execution plan defines how the itriX website MVP will be built, reviewed, tested, and privately launched.

The purpose of the website is not to function as a traditional corporate homepage. The website must become the first working layer of the AI-powered sales platform.

The website should help selected strategic visitors:

- understand the core thesis of itriX;

- describe their compute bottleneck in non-confidential terms;

- receive an immediate and intelligent response;

- be routed to ALPHA Compute, ALPHA Core, or both;

- receive a case-specific ALPHA result page or briefing;

- be classified by product route, commercial path, and lead tier;

- move toward NDA, paid evaluation, PoC, integration, license-out, or strategic partnership.

The execution goal is simple:

Convert a serious visitor’s compute bottleneck into a confidential commercial conversation.

2. Core Build Principle

The website must be built around the following thesis:

Do not scale inefficient computation.
Make computation worth scaling first.

This message should guide the homepage, product pages, AI intake flow, personalized result page, lead scoring, dashboard, and follow-up process.

The website should not show a visible concierge, avatar, robot, salesperson, or game-like character.

The concierge function should appear through behavior:

- immediate response;

- intelligent prompt design;

- problem mirroring;

- structural diagnosis;

- ALPHA route recommendation;

- license pathway recommendation;

- lead scoring;

- case-specific result page;

- timely human follow-up.

The governing principle is:

No visible concierge. Intelligence through behavior.

3. Build Scope

3.1 Pages to Build for MVP

Public Pages

- Homepage

- ALPHA Compute

- ALPHA Core

- Non-Exclusive License-Out Pathway

- Exclusive License-Out Pathway

- Proof Preview

- Industries / Customer Pathways

- About itriX

- Contact / Review Entry

Dynamic Pages

- Personalized ALPHA Result Page

- ALPHA Compute Assessment Page

- ALPHA Core Runtime Fit Page

- Non-Exclusive Evaluation Page

- Exclusive Rights Discussion Page

- NDA-Gated Proof Preview Page

- Paid Evaluation Landing Page

4. Workstreams

Workstream 1: Project Coordination and Approval Control

Owner: Stacey

Purpose:

To coordinate schedule, task tracking, approvals, feedback consolidation, and delivery discipline.

Key responsibilities:

- maintain master task board;

- maintain decision log;

- maintain approval tracker;

- coordinate team meetings;

- collect feedback in one place;

- prevent scattered feedback;

- track daily progress;

- escalate delays;

- confirm final deliverables.

Primary outputs:

- master project dashboard;

- daily status update;

- weekly decision memo;

- approval log;

- final delivery checklist.

Workstream 2: Brand and Message Consistency

Owner: Jiin

Purpose:

To ensure that all website content reflects the itriX brand direction and does not become generic, over-technical, or overly sales-driven.

Key responsibilities:

- homepage copy refinement;

- ALPHA Compute page copy;

- ALPHA Core page copy;

- product split language;

- CTA language;

- investor / media / research wording;

- Korean-English terminology consistency if needed;

- final proofreading.

Primary outputs:

- final homepage copy;

- ALPHA Compute page copy;

- ALPHA Core page copy;

- pathway copy;

- CTA copy set;

- glossary of approved terms.

Workstream 3: Visual Identity and UI Design

Owner: Yein

Purpose:

To translate the itriX brand story into a premium, scientific, enterprise-grade website interface.

Key responsibilities:

- coordinate with external designer;

- apply square-based visual system;

- avoid generic AI graphics;

- avoid robot, avatar, game-like, or visible concierge imagery;

- create prompt interface design;

- design product split cards;

- design personalized result page;

- design proof preview cards;

- design license pathway visual;

- design dashboard UI if required.

Primary outputs:

- homepage visual direction;

- wireframe-to-design conversion;

- UI component set;

- design system draft;

- result page mockup;

- developer-ready design files.

Workstream 4: AI Sales Engine and MVP Logic

Owner: Fidel

Purpose:

To own the working logic of the AI-powered sales platform.

Key responsibilities:

- define end-to-end MVP flow;

- implement or supervise AI intake logic;

- define product routing;

- define license pathway routing;

- define lead scoring;

- define personalized result page logic;

- define CRM flow;

- confirm private launch readiness.

Primary outputs:

- AI intake flow;

- routing logic;

- lead scoring rules;

- result page logic;

- MVP readiness checklist;

- private launch test plan.

Workstream 5: Knowledge Core and Technical Accuracy

Owner: Benjamin

Purpose:

To make sure the AI response system and website content are technically safe, accurate, and disclosure-controlled.

Key responsibilities:

- build Knowledge Core structure;

- collect approved ALPHA Compute explanation;

- collect approved ALPHA Core explanation;

- collect AXIOM / CRE / FQNM explanation;

- classify knowledge by disclosure level;

- define prohibited claims;

- define NDA-only claims;

- prevent hallucination;

- approve technical wording.

Primary outputs:

- Knowledge Core v1;

- public / controlled public / NDA-only / internal-only classification;

- prohibited claims list;

- approved technical explanations;

- AI response guardrails.

Workstream 6: Visitor Journey, Briefing, and Follow-Up Operation

Owner: Naomi

Purpose:

To make sure the website experience connects to real follow-up and commercial conversion.

Key responsibilities:

- define visitor journey map;

- prepare result page text logic;

- prepare briefing templates;

- prepare follow-up emails;

- define human follow-up rules;

- define Success Team process;

- define meeting agenda;

- define paid evaluation transition.

Primary outputs:

- visitor journey map;

- personalized result page content;

- follow-up email templates;

- first meeting agenda;

- paid evaluation transition guide;

- Success Team operating checklist.

Workstream 7: Research, QA, and Private Launch Support

Owner: Ezra

Purpose:

To support execution through research, QA testing, scenario preparation, and private launch readiness.

Key responsibilities:

- research target visitors;

- prepare 20 private MVP invitee candidates;

- research comparable websites;

- prepare test prompts;

- test AI intake results;

- record issues;

- support QA;

- summarize private launch feedback.

Primary outputs:

- strategic visitor list;

- competitor / benchmark notes;

- test prompt library;

- QA log;

- private launch feedback summary.

5. Approval Roles

5.1 Strategic Approval

Approver: Park Dae-hyuk

Approves:

- core thesis;

- homepage direction;

- brand positioning;

- product positioning;

- commercial pathway direction;

- final MVP launch decision.

5.2 CEO Approval

Approver: CEO Kang

Approves:

- public-facing strategic message;

- ALPHA Compute and ALPHA Core positioning;

- license-out pathway language;

- investor / partner / media-sensitive claims;

- final private MVP release.

5.3 Technical Approval

Approver: itriX technical owner / Benjamin coordination

Approves:

- technical descriptions;

- AXIOM / CRE / FQNM wording;

- proof preview wording;

- claims related to performance, reproducibility, memory, energy, or execution;

- NDA-only classification;

- prohibited claims.

5.4 Operational Approval

Approver: Fidel / Stacey

Approves:

- MVP flow readiness;

- CRM setup;

- dashboard readiness;

- human follow-up process;

- private launch operating readiness.

6. Core Deliverables

6.1 Strategy and Content Deliverables

- Final homepage copy

- ALPHA Compute page copy

- ALPHA Core page copy

- Non-exclusive license-out page copy

- Exclusive license-out page copy

- Proof preview copy

- Industries / customer pathway copy

- About itriX page copy

- CTA copy library

- Follow-up email templates

6.2 UX and Design Deliverables

- Homepage wireframe

- Prompt interface design

- Product split cards

- Structural diagnosis cards

- Proof preview cards

- License pathway visuals

- Personalized result page design

- Paid evaluation landing page design

- Dashboard UI draft

- Mobile-responsive design

6.3 AI and Functional Deliverables

- AI intake opening message

- Qualification questions

- Product routing logic

- License pathway routing logic

- Lead scoring formula

- Result page generation logic

- Internal lead summary template

- CRM capture logic

- Human follow-up routing

- Safety and disclosure guardrails

6.4 Operations Deliverables

- CRM setup

- Lead dashboard

- Owner assignment rule

- Tier 1 / Tier 2 / Tier 3 response rule

- NDA escalation rule

- Paid evaluation transition rule

- Exclusive pathway approval checklist

- Private MVP invitee list

- Private launch feedback form

- Launch readiness checklist

7. Ten-Day Build Sprint

Day 1 — Finalize Core Direction and Homepage Copy

Owner: Jiin
Support: Stacey, Fidel, Yein

Deliverables:

- final homepage headline;

- sub-headline;

- prompt section copy;

- product split copy;

- structural problem copy;

- CTA language;

- NDA warning text.

Decision required:

- approve homepage core thesis;

- confirm “Do not scale inefficient computation. Make computation worth scaling first.”

Day 2 — Finalize ALPHA Compute and ALPHA Core Pages

Owner: Jiin
Support: Benjamin, Fidel

Deliverables:

- ALPHA Compute page copy;

- ALPHA Core page copy;

- product positioning;

- target visitor descriptions;

- CTA copy;

- disclosure-safe technical wording.

Decision required:

- approve public explanation of ALPHA Compute;

- approve public explanation of ALPHA Core.

Day 3 — Finalize License-Out Pathway Pages

Owner: Naomi
Support: Fidel, Jiin, Stacey

Deliverables:

- Non-Exclusive License-Out page copy;

- Exclusive License-Out page copy;

- commercial flow diagrams;

- exclusive pathway guardrails;

- CTA language;

- internal approval checklist.

Decision required:

- confirm non-exclusive as default path;

- confirm exclusive as premium strategic path;

- approve exclusivity guardrails.

Day 4 — Finalize Personalized ALPHA Result Page

Owner: Naomi
Support: Fidel, Benjamin, Yein

Deliverables:

- result page structure;

- personalized hero template;

- problem mirror template;

- structural diagnosis table;

- product route copy;

- license path recommendation;

- KPI preview;

- proof preview;

- recommended next step logic.

Decision required:

- approve result page content structure.

Day 5 — Finalize AI Intake Prompt and Qualification Flow

Owner: Fidel
Support: Benjamin, Naomi

Deliverables:

- opening message;

- first prompt;

- qualification questions;

- answer options;

- NDA warning logic;

- sparse input response;

- complex technical input response.

Decision required:

- approve number of questions for MVP;

- confirm no confidential technical detail before NDA.

Day 6 — Finalize Routing and Lead Scoring Logic

Owner: Fidel
Support: Naomi, Benjamin

Deliverables:

- ALPHA Compute routing rules;

- ALPHA Core routing rules;

- Both-route logic;

- non-exclusive routing rules;

- exclusive routing rules;

- strategic partnership routing rules;

- lead scoring formula;

- tier actions.

Decision required:

- approve scoring weights;

- approve tier thresholds;

- approve human handoff triggers.

Day 7 — Build CRM and Human Follow-Up Dashboard Spec

Owner: Fidel
Support: Stacey, Naomi

Deliverables:

- CRM fields;

- dashboard fields;

- status values;

- owner assignment rules;

- dashboard filters;

- follow-up actions;

- escalation rules.

Decision required:

- confirm CRM tool or temporary dashboard tool;

- approve response-time commitments.

Day 8 — Finalize Paid Evaluation Packages

Owner: Naomi
Support: Jiin, Fidel, Benjamin

Deliverables:

- ALPHA Compute Bottleneck Assessment package;

- ALPHA Core Runtime Fit Assessment package;

- Combined ALPHA Evaluation package;

- deliverables list;

- suggested meeting agenda;

- paid evaluation transition script.

Decision required:

- approve package names;

- approve scope of each package;

- decide whether pricing is disclosed or withheld.

Day 9 — Designer / Developer Handoff

Owner: Yein
Support: Stacey, Fidel, Jiin

Deliverables:

- final wireframe;

- UI design brief;

- visual direction;

- page list;

- component list;

- content files;

- interaction notes;

- responsive requirements.

Decision required:

- approve design brief;

- approve first visual direction.

Day 10 — Complete Build Handoff Package

Owner: Stacey
Support: All

Deliverables:

- full build package;

- content folder;

- design folder;

- AI prompt / routing folder;

- CRM / dashboard folder;

- Knowledge Core folder;

- test prompt folder;

- private launch checklist.

Decision required:

- confirm MVP build readiness;

- assign build execution owners;

- confirm private launch date.

8. Development Sprint After Build Package

After the 10-day build package is completed, the developer should proceed through the following build sprint.

Sprint 1 — Static Website Pages

Build:

- Homepage

- ALPHA Compute

- ALPHA Core

- Non-Exclusive License-Out

- Exclusive License-Out

- Proof Preview

- About itriX

- Contact / Review Entry

Acceptance criteria:

- all pages load correctly;

- copy is implemented accurately;

- CTA buttons work;

- mobile view is acceptable;

- no unapproved claims are added.

Sprint 2 — Prompt Interface and Intake Flow

Build:

- prompt input;

- example prompts;

- qualification questions;

- NDA warning;

- immediate response;

- basic classification;

- submission confirmation.

Acceptance criteria:

- visitor can submit bottleneck;

- no long pause after submission;

- confidentiality warning appears before deeper details;

- initial response appears quickly.

Sprint 3 — ALPHA Routing and Result Page

Build:

- ALPHA Compute / ALPHA Core / Both routing;

- non-exclusive / exclusive / strategic routing;

- personalized result page;

- structural diagnosis table;

- KPI preview;

- recommended next step.

Acceptance criteria:

- result page is generated;

- result page does not overpromise;

- product route is logical;

- commercial path is displayed clearly.

Sprint 4 — CRM and Dashboard

Build:

- CRM record creation;

- lead scoring;

- dashboard;

- status tracking;

- owner assignment;

- internal notes;

- lead tier display.

Acceptance criteria:

- every submission creates a record;

- lead score is calculated;

- owner can be assigned;

- status can be updated;

- dashboard can filter by lead tier and status.

Sprint 5 — Email and Follow-Up

Build:

- confirmation email;

- review brief email;

- internal notification;

- follow-up template;

- meeting request link or manual meeting process.

Acceptance criteria:

- visitor receives confirmation;

- internal team receives alert;

- Tier 1 and Tier 2 leads are flagged;

- email text is approved.

Sprint 6 — QA and Private Launch Readiness

Build / test:

- test prompts;

- routing accuracy;

- lead scoring accuracy;

- mobile responsiveness;

- form submission;

- CRM records;

- email delivery;

- result page quality;

- prohibited claim checks.

Acceptance criteria:

- all critical user flows work;

- no visible concierge or chatbot character appears;

- no confidential details are requested before NDA;

- no unsupported claims appear;

- private launch list is ready.

9. Private MVP Launch Plan

9.1 Launch Type

The first launch should be private.

The website should not be broadly promoted until the conversion flow has been tested with selected strategic visitors.

9.2 Target Invitees

Prepare approximately 20 hand-selected strategic visitors.

Target categories:

- semiconductor executives;

- hyperscaler contacts;

- HPC / CAE leaders;

- AI infrastructure partners;

- energy-aware infrastructure contacts;

- strategic investors;

- public AI infrastructure contacts;

- selected researchers or technical validators.

Owner: Ezra
Approval: Park Dae-hyuk / Stacey

9.3 Launch Targets

| Metric | Target |
| --- | --- |
| Strategic visitors invited | 20 |
| Completed ALPHA assessments | 10 |
| Human follow-up meetings | 5 |
| NDA discussions | 2 |
| Paid evaluation candidates | 1 |
| Strategic feedback interviews | 5 |

10. Human Follow-Up Rules

10.1 Tier 1 Strategic Lead

Score: 80–100
Response time: within 24 hours

Actions:

- Review AI-generated summary.

- Confirm company and role.

- Confirm ALPHA route.

- Confirm commercial pathway.

- Send personalized follow-up.

- Offer confidential meeting.

- Prepare NDA if appropriate.

- Recommend paid evaluation if fit is confirmed.

- Escalate exclusive or strategic requests.

10.2 Tier 2 Qualified Lead

Score: 60–79
Response time: within 48 hours

Actions:

- Send personalized summary.

- Ask one clarifying question.

- Offer discovery call.

- Recommend paid assessment if workload fit is plausible.

10.3 Tier 3 Nurture Lead

Score: 40–59
Response time: automated within 24 hours

Actions:

- Send educational or strategic brief.

- Offer future update.

- Re-score if visitor returns or provides more information.

10.4 Tier 4 Low-Fit Lead

Score: 0–39

Actions:

- Provide educational content only.

- No human follow-up unless the visitor later provides stronger fit signals.

11. Risk Management

Risk 1: Technical claims are not approved

Mitigation:

- Benjamin owns technical approval.

- No proof or performance claim goes live without approval.

- Use disclosure classifications: Public, Controlled Public, NDA-Only, Internal-Only, Prohibited.

Risk 2: Website becomes too sales-like

Mitigation:

- Avoid aggressive CTA language.

- Use review, evaluation, briefing, and pathway language.

- Do not push “Contact Sales.”

- Maintain premium, scientific, strategic tone.

Risk 3: ALPHA Compute and ALPHA Core become confused

Mitigation:

- ALPHA Compute = representation-layer transformation.

- ALPHA Core = execution engine.

- Use product split consistently.

- Route visitors clearly.

Risk 4: Exclusive rights are offered too casually

Mitigation:

- Non-exclusive is default.

- Exclusive requires approval checklist.

- Exclusivity must be narrow, time-bound, milestone-bound, and commercially justified.

Risk 5: AI intake over-discloses or hallucinates

Mitigation:

- Knowledge Core controls responses.

- Prohibited claims list required.

- NDA warning displayed.

- Technical claims routed to review.

Risk 6: Human follow-up is too slow

Mitigation:

- Tier 1 response within 24 hours.

- Tier 2 response within 48 hours.

- CRM alerts and owner assignment required.

Risk 7: Private launch visitors are not high quality

Mitigation:

- Ezra prepares invitee list.

- Park Dae-hyuk approves strategic visitor list.

- Focus on quality over quantity.

12. Immediate Action List

Within 24 Hours

- Stacey opens master task board.

- Stacey creates approval tracker.

- Fidel confirms MVP flow owner list.

- Benjamin requests technical source materials.

- Naomi finalizes follow-up workflow.

- Jiin finalizes homepage copy direction.

- Yein briefs designer on visual direction.

- Ezra starts strategic visitor list.

Within 48 Hours

- Homepage copy draft completed.

- ALPHA Compute / ALPHA Core copy draft completed.

- AI intake question set finalized.

- CRM fields finalized.

- Designer receives wireframe brief.

- Knowledge Core source material request sent to itriX technical team.

Within 72 Hours

- First homepage design concept.

- Product page copy ready for review.

- Result page template ready.

- Routing and scoring logic ready.

- Follow-up email templates ready.

- Private MVP invitee list first draft ready.

13. Final Acceptance Criteria

The build is ready for private MVP launch when:

- Homepage communicates the core thesis clearly.

- Visitor can describe compute bottleneck in non-confidential terms.

- Immediate response appears without long pause.

- Qualification flow works.

- ALPHA Compute / ALPHA Core / Both routing works.

- Non-exclusive / exclusive / strategic pathway routing works.

- Personalized result page is generated.

- Lead score and lead tier are calculated.

- CRM record is created.

- Human follow-up owner is assigned.

- Tier 1 and Tier 2 response rules are operational.

- NDA warning appears before sensitive detail collection.

- Paid evaluation packages are defined.

- Exclusive pathway approval checklist is operational.

- Technical claims are approved or properly gated.

- No visible concierge, avatar, robot, or game-like character appears.

- The experience feels premium, scientific, strategic, minimal, and trustworthy.

14. Final Execution Statement

The itriX website build should not be judged by how much information it displays.

It should be judged by whether it can turn a serious visitor’s compute bottleneck into a clear ALPHA route, a qualified commercial pathway, and a confidential next conversation.

The first MVP is successful if it can help itriX move selected strategic visitors from curiosity to NDA, paid evaluation, PoC, integration, and license-out discussion.