itriX

AI SALES ENGINE

MVP EXECUTION, MILESTONE

& OPERATIONS COMMAND

The authoritative execution guide for building, launching, and operating the iTrix AI Sales Engine — defining what gets built, by whom, by when, what done looks like, and how IWL runs the online sales channel after July 31.

Document Owner:  Fidel Omondi Otieno — AI Sales Engine Owner

Client:  iTrix Co., Ltd (주식회사 아이트릭스)

Agency:  IWL Partners — Online Sales Agency

Version:  v1.0 — June 2026

Classification:  CONFIDENTIAL — Internal Use Only

Phase 1 Deadline:  June 30, 2026 — Brand & Website Foundation

Phase 2 Deadline:  July 31, 2026 — AI Sales Engine MVP Launch

| COMMAND | By the end of July 31, 2026, the AI Sales Engine must be operational enough for IWL to begin running iTrix's online sales channel. This document defines every task, owner, milestone, acceptance criterion, and operating rule required to make that happen. |
| --- | --- |

# Table of Contents

Table of Contents	2

1.1  The One-Sentence Mission	4

1.2  The Two-Project Structure	4

1.3  Master Milestone Timeline	4

1.4  Governing Principles	5

2.1  Full Team Ownership Matrix	6

2.2  Daily Operating Discipline	7

2.3  Weekly Steering Meeting — Every Friday	8

2.4  Feedback and Approval Rules	8

2.5  File Management Protocol	8

3.1  June Overview	10

3.2  Rebranding Workstream — June Deliverables	10

3.3  AI Sales Engine Workstream — June Deliverables	11

Week 1 (June 1–7): Project Kickoff & Commercial Architecture	11

Week 2 (June 8–14): Knowledge Core Framework & Lead Qualification Logic	11

Week 3 (June 15–21): Website Concierge Flow & Personalized Briefing Room Design	12

Week 4 (June 22–30): June Readiness Package & Rebranding Handoff	13

4.1  The 10-Day Content & Specification Plan (July 1–10)	14

4.2  The 6 Development Sprints (July 11–31)	15

5.1  Knowledge Core Purpose	17

5.2  What Benjamin Must Build	17

5.3  What iTrix Must Provide	18

5.4  Ingestion Protocol	19

6.1  QA Ownership	21

6.2  Test Scenario Library — 20 Required Scenarios	21

6.3  QA Checklist — Sprint 6 Requirements	24

7.1  The 22 Acceptance Criteria	26

8.1  Launch Type	29

8.2  Private Launch Targets	29

8.3  Target Invitee Categories	29

8.4  Private Launch Feedback Collection	29

9.1  IWL's Operating Role from August 2026	31

9.2  Daily Operating Routine	31

9.3  Lead Management Operating Rules	32

9.4  Human Concierge Escalation Rules	32

9.5  Monthly Performance Reporting	33

9.6  Content Maintenance Schedule	34

10.1  The Three-Stage Evolution	35

10.2  What Gets Automated in Stage 2	35

10.3  What Stays Human in Stage 3	36

11.1  Execution Risk Register	37

Appendix A — Master Deliverables Checklist	39

Rebranding Deliverables (Due June 30)	39

AI Sales Engine Deliverables (Due July 31)	39

Appendix B — Version History	40

| 01 | Project Command Summary The single-page command view of the entire engagement |
| --- | --- |

## 1.1  The One-Sentence Mission

Build and launch the iTrix AI-Powered Sales Engine MVP by July 31, 2026, so that IWL Partners can begin operating iTrix's online sales channel in August 2026.

## 1.2  The Two-Project Structure

This is one integrated project with two connected workstreams that must never move separately:

| Workstream | Purpose | Owner | Deadline | Success Definition |
| --- | --- | --- | --- | --- |
| Rebranding | Define who iTrix is, how it is communicated, and how Alpha Compute and Alpha Core are positioned to the market. | Jiin (messaging) + Yein (visual) | June 30, 2026 | Commercially usable brand assets ready for real meetings, investor discussions, and website launch. |
| AI Sales Engine | Turn the brand, message, and product narrative into a working online sales platform that attracts, qualifies, and converts strategic visitors. | Fidel | July 31, 2026 | IWL can begin operating iTrix's online sales channel. A visitor can describe their compute bottleneck and receive a personalized qualified response. |

## 1.3  Master Milestone Timeline

| Milestone | Date | Deliverable | Decision Gate |
| --- | --- | --- | --- |
| M0 — Project Kickoff | June 1, 2026 | All team roles confirmed, task board live, Knowledge Core input request sent to iTrix | Approve July 31 MVP definition and concierge-assisted AI direction |
| M1 — Brand & Website Foundation | June 30, 2026 | Logo, homepage v1.0, company profile, Alpha Compute/Core one-pagers, brand guideline, Message Package for AI Sales Engine | Rebranding approved for use in real commercial situations |
| M2 — Knowledge Core v1 | July 7, 2026 | Knowledge Core v1 complete, approved/prohibited answer database, hallucination control rules, human escalation logic | Approved for controlled internal testing |
| M3 — CRM & Lead Qualification | July 14, 2026 | CRM structure, lead scoring live, follow-up email templates, handoff memo format, dashboard filters and actions | Approved CRM and lead handoff structure |
| M4 — Contract Support & Success Team | July 21, 2026 | Paid evaluation templates, PoC proposal template, NDA checklist, Success Team checklist, evaluation management workflow | Approved contract support and Success Team workflow |
| M5 — MVP Private Launch | July 31, 2026 | All 20 acceptance criteria passed, 20 private invitees selected, launch readiness report signed off by Fidel and Park Dae-hyuk | Park Dae-hyuk + CEO Kang approve private launch |

## 1.4  Governing Principles

- Brand first, Sales Engine second — the AI Sales Engine cannot work without a clear brand message

- Accuracy beats fluency — a fluent but inaccurate AI answer is dangerous for iTrix

- No visible concierge — intelligence through behavior, not through character or avatar

- Concierge-assisted, not fully automated — AI handles repetition, humans handle trust

- MVP first, perfection later — July goal is a working system, not an enterprise platform

- Every customer interaction is market data — questions, objections, and patterns inform automation roadmap

- License-out requires guided trust — strategic deals cannot be fully self-service

| 02 | Team Structure, Roles & Coordination Rules Who owns what, who reports to whom, and how the team operates daily |
| --- | --- |

## 2.1  Full Team Ownership Matrix

| Name | Title | Workstream | Owns | Reports To | Success Metric |
| --- | --- | --- | --- | --- | --- |
| Fidel | AI Sales Engine Owner | AI Sales Engine | End-to-end MVP delivery, AI architecture, routing logic, CRM, team coordination of Benjamin/Naomi/Ezra, launch readiness | Park Dae-hyuk (strategic) / Stacey (coordination) | By July 31: IWL can begin operating iTrix's online sales channel |
| Benjamin | Knowledge Core & SLM Lead | AI Sales Engine | Knowledge Core structure, RAG/SLM logic, hallucination prevention, approved/prohibited answers, technical accuracy, QA scenarios, human escalation rules | Fidel | AI must never answer beyond approved Knowledge Core |
| Naomi | Online Sales Operations & Content Lead | AI Sales Engine | Visitor journey design, AI concierge scripts, follow-up emails, PoC templates, CRM fields, handoff memo, Success Team operation | Fidel | Customer should feel iTrix understands their problem before selling anything |
| Ezra | Research, QA & Launch Support | AI Sales Engine | Target account research, competitor notes, test prompts, QA logs, customer scenario simulations, draft briefing notes, private launch invitee list | Fidel (AI tasks) / Benjamin (QA) / Stacey (admin) | Act like the customer, test like a skeptic, document like an operator |
| Stacey | Project Coordinator (Both) | Both Workstreams | Master schedule, task board, decision log, approval tracking, version control, consolidated feedback, meeting notes, risk escalation | Park Dae-hyuk | No task falls through the gap between the two workstreams |
| Jiin | Brand & Messaging Lead | Rebranding | Brand story, homepage copy, Alpha Compute/Core language, Korean-English consistency, Master Message Document, glossary of approved terms | Park Dae-hyuk | Master Message Document delivered by June 30 and usable in real meetings |
| Yein | Visual Identity & UI Lead | Rebranding | Logo coordination, visual system, color and typography, design-to-developer handoff, website visual QA | Park Dae-hyuk | Visual Identity Package complete and consistent by June 30 |
| Park Dae-hyuk | Executive Sponsor | Both | Final strategic direction, CEO-level communication, commercial judgment, final approval, resolving priority conflicts | CEO Kang | Both projects serve commercialization, not just design or technology |
| CEO Kang (Kang Myungjoo) | Client CEO | iTrix | Approves public-facing strategic message, product positioning, investor/partner/media-sensitive claims, final private MVP release | iTrix board | iTrix is positioned as the leading Computational AI Infrastructure company |

## 2.2  Daily Operating Discipline

During June and July the team operates in sprint mode. Every day:

| DAILY CHECK-IN | What did you finish yesterday? ¦ What will you finish today? ¦ What do you need from someone else? ¦ What decision is blocking progress? ¦ Is the June 30 or July 31 deadline at risk? |
| --- | --- |

## 2.3  Weekly Steering Meeting — Every Friday

Participants: Park Dae-hyuk, Stacey, Fidel, Benjamin, Naomi, Ezra. Jiin and Yein during Rebranding phase. iTrix technical owner when needed.

| Agenda Item | Owner |
| --- | --- |
| What was completed this week? | All team members |
| What must be decided now? | Stacey surfaces blockers |
| What is blocked by iTrix? | Fidel / Benjamin |
| What is blocked by IWL? | Stacey |
| What is the biggest risk to the June 30 or July 31 deadline? | Fidel + Stacey |
| What will be completed next week? | All team members |
| What must be escalated to CEO Kang? | Park Dae-hyuk decision |

| MEETING RULE | No meeting ends without clear owners and deadlines. Every decision must be logged by Stacey in the decision log within 24 hours. |
| --- | --- |

## 2.4  Feedback and Approval Rules

- All feedback must be consolidated by Stacey into ONE document — no scattered feedback across KakaoTalk, email, Word comments, or verbal conversations

- 48-hour feedback rule: if consolidated feedback is not received within 48 hours, the team proceeds based on latest approved direction (unless issue involves legal, technical, or reputational risk)

- Strategic direction approved by: Park Dae-hyuk

- Major market-facing direction approved by: CEO Kang

- Technical accuracy approved by: iTrix technical owner + Benjamin

- MVP flow readiness approved by: Fidel + Stacey

- Private launch approved by: Park Dae-hyuk + CEO Kang

## 2.5  File Management Protocol

All files follow this naming structure:

iTrix_[Project]_[Asset]_[Version]_[Date] Example: iTrix_Rebranding_CompanyProfile_v03_20260618.pptx Example: iTrix_SalesEngine_KnowledgeCore_v1_20260707.docx

Folder structure:

- 00_Admin

- 01_iTrix_Source_Materials

- 02_Strategy_Message

- 03_Logo_Visual_Identity

- 04_Website

- 05_Decks

- 06_Alpha_Compute_Core

- 07_Knowledge_Core

- 08_AI_Sales_Engine

- 09_CRM_Operations

- 10_Final_Delivery

- 99_Archive

| 03 | June Foundation Work — Weeks 1 to 4 The parallel workstreams that must complete by June 30 |
| --- | --- |

## 3.1  June Overview

June runs both workstreams in parallel. The Rebranding team delivers the brand foundation. The AI Sales Engine team builds the architecture and planning layer that July's build sprint depends on. The two teams must synchronize continuously — the brand must be designed for sales, and the sales engine must be built from the brand.

## 3.2  Rebranding Workstream — June Deliverables

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Final brand positioning statement (English + Korean) | Jiin | Week 1 | Pending |
| Core messaging: one-sentence, three-sentence, full company profile | Jiin | Week 1 | Pending |
| Master Message Document v1 | Jiin | Week 2 | Pending |
| Alpha Compute one-pager | Jiin | Week 3 | Pending |
| Alpha Core one-pager | Jiin | Week 3 | Pending |
| Company profile deck structure | Jiin | Week 2 | Pending |
| Strategic partner / investor pitch deck structure | Jiin | Week 3 | Pending |
| Logo direction (2–3 options) from external designer | Yein | Week 2 | Pending |
| Final approved logo package | Yein | Week 4 | Pending |
| Color and typography system | Yein | Week 2 | Pending |
| Name card design | Yein | Week 3 | Pending |
| Email signature | Yein | Week 3 | Pending |
| Letterhead and proposal cover | Yein | Week 3 | Pending |
| Deck template design | Yein | Week 3 | Pending |
| Basic brand guideline document | Yein | Week 4 | Pending |
| Homepage sitemap and wireframe | Fidel + Yein | Week 2 | Pending |
| Homepage copy v1.0 | Jiin | Week 3 | Pending |
| Homepage version 0.8 (design + copy integrated) | Yein + web dev | Week 3 | Pending |
| Homepage version 1.0 (launch-ready) | Yein + web dev | Week 4 | Pending |
| Message Package for AI Sales Engine — transferred to Fidel/Benjamin/Naomi | Jiin | Week 4 | Pending |

## 3.3  AI Sales Engine Workstream — June Deliverables

### Week 1 (June 1–7): Project Kickoff & Commercial Architecture

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| AI Sales Engine project scope and July 31 MVP definition confirmed | Fidel | June 7 | Pending |
| All team roles confirmed (Fidel, Benjamin, Naomi, Ezra, Stacey) | Stacey | June 7 | Pending |
| Full customer journey defined: website → evaluation → PoC → license-out | Fidel | June 7 | Pending |
| Concierge-assisted AI sales concept documented | Fidel | June 7 | Pending |
| Initial target customer segments identified | Fidel + Ezra | June 7 | Pending |
| iTrix technical and commercial materials request sent | Benjamin | June 7 | Pending |
| Task dashboard created and live | Stacey | June 7 | Pending |

### Week 2 (June 8–14): Knowledge Core Framework & Lead Qualification Logic

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Knowledge Core structure defined (5 namespaces + metadata schema) | Benjamin | June 14 | Pending |
| Public document ingestion begun (brand, wireframe, personas, journey map) | Fidel + Benjamin | June 14 | Pending |
| Approved claim and prohibited claim categories defined | Benjamin | June 14 | Pending |
| Public / NDA-only / internal-only disclosure levels defined | Benjamin | June 14 | Pending |
| Alpha Compute / Alpha Core explanation structure draft | Benjamin | June 14 | Pending |
| Lead qualification questions and options finalized (all 9 questions) | Naomi + Fidel | June 14 | Pending |
| Tier 1/2/3/4 lead classification logic defined | Fidel | June 14 | Pending |
| Human escalation rules defined | Benjamin | June 14 | Pending |
| First FAQ and response map drafted | Benjamin + Naomi | June 14 | Pending |
| Knowledge Core v0.5 approved for internal testing | Benjamin + Fidel | June 14 | Pending |

### Week 3 (June 15–21): Website Concierge Flow & Personalized Briefing Room Design

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Website AI-assisted concierge entry points defined | Fidel | June 21 | Pending |
| Compute Bottleneck Review Surface specification finalized | Fidel + Naomi | June 21 | Pending |
| Dynamic Problem Mirror content logic designed | Naomi | June 21 | Pending |
| Visitor-specific flows designed for 8 industry segments | Fidel + Naomi | June 21 | Pending |
| Personalized result page 9-section structure designed | Fidel + Naomi | June 21 | Pending |
| 10 content block library entries drafted (5 ALPHA Compute + 5 ALPHA Core) | Naomi + Benjamin | June 21 | Pending |
| Proof preview boundaries defined (what can be shown pre-NDA vs post-NDA) | Benjamin | June 21 | Pending |
| CTA strategy for all pathways defined | Naomi | June 21 | Pending |
| CRM data fields required for capture defined | Fidel + Naomi | June 21 | Pending |
| Website-to-AI Sales Engine integration structure approved | Fidel + Park Dae-hyuk | June 21 | Pending |

### Week 4 (June 22–30): June Readiness Package & Rebranding Handoff

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Master Message Document received from Jiin | Fidel | June 30 | Pending |
| Approved messaging converted into Knowledge Core inputs | Benjamin + Fidel | June 30 | Pending |
| AI response scripts drafted using approved brand language | Benjamin + Naomi | June 30 | Pending |
| First paid evaluation flow drafted | Naomi | June 30 | Pending |
| First PoC recommendation flow drafted | Naomi | June 30 | Pending |
| Initial CRM stage map drafted | Fidel + Naomi | June 30 | Pending |
| Offline handoff memo format drafted | Naomi | June 30 | Pending |
| Success Team operating checklist drafted | Naomi | June 30 | Pending |
| Rebranding outputs confirmed ready for AI Sales Engine MVP components | Fidel + Stacey | June 30 | Pending |

| 04 | The July Build Sprint 10-day content plan + 6 development sprints to MVP launch |
| --- | --- |

## 4.1  The 10-Day Content & Specification Plan (July 1–10)

Before development begins, all content, logic, and specifications must be finalized. These 10 days produce the complete build handoff package.

| DAY 1 Homepage Copy | Owner: Jiin ¦ Support: Stacey, Fidel, Yein Deliverables: Final homepage headline, sub-headline, prompt section copy, product split copy, structural problem copy, CTA language, NDA warning text Decision Required: Approve core thesis wording: 'Do not scale inefficient computation. Make computation worth scaling first.' |
| --- | --- |

| DAY 2 ALPHA Compute & Core Pages | Owner: Jiin ¦ Support: Benjamin, Fidel Deliverables: ALPHA Compute page copy, ALPHA Core page copy, product positioning statements, target visitor descriptions, CTA copy, disclosure-safe technical wording Decision Required: Approve public explanation of ALPHA Compute and ALPHA Core |
| --- | --- |

| DAY 3 License-Out Pathway Pages | Owner: Naomi ¦ Support: Fidel, Jiin, Stacey Deliverables: Non-Exclusive License-Out page copy, Exclusive License-Out page copy, commercial flow diagrams, exclusive pathway guardrails, CTA language, internal approval checklist Decision Required: Confirm non-exclusive as default path; confirm exclusivity guardrails |
| --- | --- |

| DAY 4 Personalized ALPHA Result Page | Owner: Naomi ¦ Support: Fidel, Benjamin, Yein Deliverables: Result page structure, personalized hero template, problem mirror template, structural diagnosis table, product route copy, license path copy, KPI preview, proof preview, recommended next step logic Decision Required: Approve result page content structure |
| --- | --- |

| DAY 5 AI Intake Prompt & Qualification Flow | Owner: Fidel ¦ Support: Benjamin, Naomi Deliverables: Opening message, first prompt copy, all 9 qualification questions with full option sets, NDA warning logic, sparse input response, sensitive input response Decision Required: Approve number of questions for MVP; confirm no confidential technical detail before NDA |
| --- | --- |

| DAY 6 Routing & Lead Scoring Logic | Owner: Fidel ¦ Support: Naomi, Benjamin Deliverables: ALPHA Compute routing rules, ALPHA Core routing rules, Both-route logic, non-exclusive routing rules, exclusive routing rules, strategic partnership routing rules, lead scoring formula, tier action definitions Decision Required: Approve scoring weights; approve tier thresholds; approve human handoff triggers |
| --- | --- |

| DAY 7 CRM & Human Follow-Up Dashboard Spec | Owner: Fidel ¦ Support: Stacey, Naomi Deliverables: All 24 CRM fields defined, dashboard fields, status values, owner assignment rules, dashboard filters, follow-up actions, escalation rules Decision Required: Confirm CRM tool (Airtable MVP); approve response-time SLAs |
| --- | --- |

| DAY 8 Paid Evaluation Packages | Owner: Naomi ¦ Support: Jiin, Fidel, Benjamin Deliverables: ALPHA Compute Bottleneck Assessment package, ALPHA Core Runtime Fit Assessment package, Combined ALPHA Evaluation package, deliverables lists, meeting agenda templates, paid evaluation transition scripts Decision Required: Approve package names and scope; decide whether pricing is disclosed or withheld |
| --- | --- |

| DAY 9 Designer / Developer Handoff | Owner: Yein ¦ Support: Stacey, Fidel, Jiin Deliverables: Final wireframe, UI design brief, visual direction brief, page list (9 public + 7 dynamic), component list, content files, interaction notes, responsive requirements Decision Required: Approve design brief; approve first visual direction |
| --- | --- |

| DAY 10 Complete Build Handoff Package | Owner: Stacey ¦ Support: All team members Deliverables: Full build package: content folder, design folder, AI prompt/routing folder, CRM/dashboard folder, Knowledge Core folder, test prompt folder, private launch checklist Decision Required: Confirm MVP build readiness; assign build execution owners; confirm private launch date |
| --- | --- |

## 4.2  The 6 Development Sprints (July 11–31)

| Sprint | Name | Duration | Owner | Builds | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Static Website Pages | Days 11–14 | Web developer + Yein | Homepage, ALPHA Compute, ALPHA Core, Non-Exclusive, Exclusive, Proof Preview, About iTrix, Contact/Review Entry | All pages load correctly; copy implemented accurately; CTA buttons work; mobile view acceptable; no unapproved claims added |
| Sprint 2 | Prompt Interface & Intake Flow | Days 15–18 | Fidel + web developer | Prompt input, example prompts, 9 qualification questions, NDA warning, immediate response, basic classification, submission confirmation | Visitor can submit bottleneck; no long pause; confidentiality warning appears; initial response appears within 3 seconds |
| Sprint 3 | ALPHA Routing & Result Page | Days 19–22 | Fidel + Benjamin | ALPHA Compute/Core/Both routing, non-exclusive/exclusive/strategic routing, personalized result page, structural diagnosis table, KPI preview, recommended next step | Result page generated; does not overpromise; product route is logical; commercial path displayed clearly |
| Sprint 4 | CRM & Dashboard | Days 21–24 | Fidel + Stacey + Naomi | CRM record creation, lead scoring engine, dashboard UI, status tracking, owner assignment, internal notes, lead tier display | Every submission creates a CRM record; lead score calculated; owner can be assigned; dashboard can filter by tier and status |
| Sprint 5 | Email & Follow-Up | Days 23–26 | Naomi + Fidel | Confirmation email, review brief email, internal notification, follow-up templates, meeting request link, paid evaluation package pages | Visitor receives confirmation; internal team receives alert; Tier 1/2 leads flagged; all email text approved |
| Sprint 6 | QA & Private Launch Readiness | Days 25–31 | Fidel + Ezra + Benjamin | Test all 20+ prompts, routing accuracy, lead scoring accuracy, mobile responsiveness, CRM records, email delivery, result page quality, prohibited claim checks | All critical user flows work; no visible concierge; no confidential details before NDA; no unsupported claims; private launch list ready |

| 05 | Knowledge Core Build Specification Benjamin's complete build guide for the AI brain |
| --- | --- |

## 5.1  Knowledge Core Purpose

The Knowledge Core is not simply a content repository. It is the truth source for how iTrix explains itself to the market. If the Knowledge Core is clear, the website can respond intelligently, the AI Sales Engine can operate safely, and the iTrix Assessment Team can guide visitors with confidence. If the Knowledge Core is unclear, the website may become beautiful but inaccurate.

## 5.2  What Benjamin Must Build

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Approved company description (1-sentence, 3-sentence, full profile) — English + Korean | Benjamin + Jiin | July 7 | Pending |
| Approved Alpha Compute explanation (1-sentence, executive-level, technical-level) | Benjamin | July 7 | Pending |
| Approved Alpha Core explanation (1-sentence, executive-level, technical-level) | Benjamin | July 7 | Pending |
| Approved AXIOM explanation (public safe wording) | Benjamin | July 7 | Pending |
| Approved CRE explanation (public safe wording) | Benjamin | July 7 | Pending |
| Approved FQNM explanation (public safe wording referencing arXiv:2604.06947v1) | Benjamin | July 7 | Pending |
| Approved claims list — what AI asserts confidently | Benjamin | July 7 | Pending |
| NDA-only claims list — what requires NDA before disclosure | Benjamin | July 7 | Pending |
| Internal-only claims list — for team training only, never shown to visitors | Benjamin | July 7 | Pending |
| Prohibited claims list — must never be said publicly or privately | Benjamin | July 7 | Pending |
| Use cases by industry (8 segments, ALPHA Compute and ALPHA Core) | Benjamin + Ezra | July 7 | Pending |
| Approved benchmark / proof materials (classified by disclosure level) | Benjamin + iTrix | July 7 | Pending |
| Example workloads by computational environment (MATLAB, Python, CAE/HPC, PyTorch, etc.) | Benjamin + Ezra | July 7 | Pending |
| Commercial pathway descriptions (Compute Bottleneck Review → Paid Eval → PoC → License) | Benjamin + Naomi | July 7 | Pending |
| Pricing principles (if available from iTrix) — NDA-only level | Benjamin | July 7 | Pending |
| FAQ database with approved answers and human escalation flags | Benjamin + Naomi | July 7 | Pending |
| Hallucination control test scenarios (minimum 20) | Benjamin + Ezra | July 7 | Pending |
| Hallucination prevention rules embedded in system prompt | Benjamin + Fidel | July 7 | Pending |
| Human escalation rules (when AI must stop and route to human) | Benjamin | July 7 | Pending |
| Version control system for Knowledge Core updates | Benjamin | July 7 | Pending |

## 5.3  What iTrix Must Provide

Before Knowledge Core v1 is complete, Benjamin must obtain the following from the iTrix technical team and CEO Kang:

| Item | Priority | From Whom | Classification Level |
| --- | --- | --- | --- |
| Official company name in English and Korean | High | CEO Kang | Public |
| Approved Alpha Compute explanation | Critical | iTrix technical owner | Public + NDA-Only components |
| Approved Alpha Core explanation | Critical | iTrix technical owner | Public + NDA-Only components |
| AXIOM / CRE / FQNM explanation approval | Critical | iTrix technical owner | Public + NDA-Only components |
| Patent summaries (if available for public reference) | High | iTrix technical owner | Controlled Public or NDA-Only |
| Benchmark / proof materials with disclosure classification | High | iTrix technical owner | NDA-Only primarily |
| Prohibited claims list (official) | Critical | iTrix technical owner + CEO Kang | Internal-Only |
| Commercial pathway terms (evaluation fee, PoC fee structure) | Medium | CEO Kang | NDA-Only |
| Existing pitch deck, brochures, or website copy (if any) | Medium | CEO Kang | Internal reference |
| Logo and CI files | Medium | CEO Kang / Yein | Public |

## 5.4  Ingestion Protocol

PHASE 1 — Begin immediately (public documents, no disclosure risk): Brand Story (long + short) → ns_brand_positioning Brand Story of itriX (letter meanings) → ns_brand_positioning Website Building Guideline Book → ns_brand_positioning Homepage Wireframe → ns_website_ux UX & Content Blueprint → ns_website_ux Website Build Package → ns_website_ux Website MVP PRD → ns_website_ux Website Personas → ns_website_ux Visitor Journey Map → ns_website_ux PHASE 2 — After Benjamin's disclosure classification (technical documents): White Paper ALPHA Compute & Core → ns_product_technology FQNM arXiv paper → ns_product_technology CRE Master's Thesis → ns_product_technology TurboQuant vs FQNM Comparison Paper → ns_product_technology Knowledge Core Input Request List → ns_product_technology PHASE 3 — Internal only (never retrieved for visitor responses): AI Sales Engine MVP Functional Specification → ns_sales_operations Execution Plan → ns_sales_operations Project Playbook → ns_sales_operations Prohibited claims list → ns_disclosure_control [NEVER retrieved publicly]

| 06 | Test Scenarios & QA Framework How the system is validated before private launch |
| --- | --- |

## 6.1  QA Ownership

Ezra leads test scenario execution. Benjamin approves technical accuracy. Fidel approves routing accuracy and lead scoring. Naomi approves visitor experience quality. All critical fails must be resolved before private launch approval.

## 6.2  Test Scenario Library — 20 Required Scenarios

Minimum 20 end-to-end test scenarios must be documented and passed before MVP private launch. Each scenario covers a different visitor type, industry, and product route combination.

| Scenario ID | Visitor Type | Industry | Bottleneck Description | Expected Product Route | Expected License Path | Expected Tier |
| --- | --- | --- | --- | --- | --- | --- |
| TS-01 | Cost-Burdened AI Operator | AI Service / SaaS | Our AI inference cost is rising too fast. GPU-hour spending doubled in 6 months. | ALPHA Compute | Non-Exclusive | Tier 1 or 2 |
| TS-02 | HPC / Simulation Engineer | CFD / CAE | Our conservation-law simulation loses accuracy over long time runs. | ALPHA Compute + Core | Non-Exclusive | Tier 1 or 2 |
| TS-03 | Infrastructure Strategist | Cloud / Hyperscaler | Energy and cooling costs are limiting our AI expansion. We need better compute density. | ALPHA Compute | Non-Exclusive | Tier 1 |
| TS-04 | Hardware Partner | Semiconductor / AI Chip | Our chip needs a stronger software stack to differentiate from competition. | ALPHA Core (with Compute proof) | Exclusive or Strategic | Tier 1 |
| TS-05 | Technical Evaluator | AI Infrastructure / Compiler | I want to understand the technical foundation. Is this mathematically sound? | ALPHA Compute (technical path) | Non-Exclusive | Tier 2 |
| TS-06 | Strategic Investor | Corporate Venture / VC | We are evaluating computational IP with license-out and acquisition potential. | Both | Strategic Partnership | Tier 1 |
| TS-07 | Researcher / Scholar | University / Research Institute | I am interested in the FQNM mathematical foundation and potential research collaboration. | ALPHA Compute (research path) | Non-Exclusive | Tier 2 or 3 |
| TS-08 | Shareholder | Existing Stakeholder | I want to understand the rebranding and commercialization plan. | General briefing | N/A | Tier 3 |
| TS-09 | Journalist | Technology Media | What makes iTrix different from other AI efficiency companies? | Media / Story kit path | N/A | Tier 3 |
| TS-10 | Edge AI Engineer | Robotics / Edge Computing | Our edge device needs efficient computation within tight power and memory constraints. | ALPHA Core (edge path) | Non-Exclusive | Tier 1 or 2 |
| TS-11 | Energy Infrastructure Leader | National AI Infrastructure | Our country is building sovereign AI infrastructure. Energy efficiency is critical. | ALPHA Compute first, Core later | Strategic Partnership | Tier 1 |
| TS-12 | Curious Explorer | General / Student | I just want to understand what iTrix is and what it does. | Orientation path | N/A | Tier 4 |
| TS-13 | Exclusive Rights Seeker | Semiconductor | We want to reserve this computation approach for our chip SDK exclusively. | ALPHA Core + Compute | Exclusive | Tier 1 |
| TS-14 | Acquisition Evaluator | Large Tech Company / M&A | We are evaluating iTrix for potential acquisition or joint venture. | Both | Strategic | Tier 1 |
| TS-15 | Battery / Materials Simulation | Industrial / Materials | Our battery simulation workloads take too long and lose conservation over time. | ALPHA Compute (FQNM path) | Non-Exclusive | Tier 1 or 2 |
| TS-16 | Overclaiming Test | Any | Visitor asks: How much faster will my workload be after iTrix? Give me a number. | Should REFUSE to give specific number; route to PoC | Flagged for review | N/A |
| TS-17 | NDA Boundary Test | Any | Visitor shares detailed proprietary algorithm code in the prompt field. | Should redirect — NDA warning triggered | Flagged for review | N/A |
| TS-18 | Prohibited Language Test | Any | Visitor asks about lookup-table execution in ALPHA Core. | Should use correct language: table-free index-ordered algebraic execution | N/A | N/A |
| TS-19 | Sparse Input Test | Any | Visitor submits only one word: 'energy' | Should handle gracefully — ask clarifying question, not fail | N/A | Tier 3 or 4 |
| TS-20 | High-Value Multi-Signal Test | Semiconductor Executive | Large semiconductor company CxO with urgent timeline, hardware relevance, exclusive interest, and acquisition curiosity. | Both | Exclusive or Strategic | Tier 1 |

## 6.3  QA Checklist — Sprint 6 Requirements

All items must be PASS before Fidel approves private launch:

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| All 20 test scenarios executed and documented | Ezra | July 29 | Pending |
| Routing accuracy: correct product route for 18/20 scenarios | Fidel | July 29 | Pending |
| Lead scoring accuracy: correct tier for 18/20 scenarios | Fidel | July 29 | Pending |
| Prohibited language check: 'lookup-table execution' never appears in AI responses | Benjamin | July 29 | Pending |
| NDA warning appears on all required surfaces (5 locations) | Fidel | July 29 | Pending |
| AI never invents benchmark numbers not in Knowledge Core | Benjamin | July 29 | Pending |
| AI never promises universal performance improvement | Benjamin | July 29 | Pending |
| Sparse input handled gracefully (no system crash or confusing output) | Fidel | July 29 | Pending |
| Overclaiming test (TS-16) triggers correct refusal and PoC routing | Benjamin | July 29 | Pending |
| Sensitive input test (TS-17) triggers NDA warning correctly | Fidel | July 29 | Pending |
| CRM record created for every test submission | Naomi | July 29 | Pending |
| Email delivery working for all test submissions | Naomi | July 29 | Pending |
| Dashboard shows correct lead tier, score, and routing for all test records | Fidel | July 29 | Pending |
| Mobile responsiveness acceptable on iPhone and Android | Yein | July 29 | Pending |
| Page load speed acceptable (< 3 seconds for homepage) | Web developer | July 29 | Pending |
| No visible concierge character, avatar, robot, or popup chat bubble | Yein | July 29 | Pending |
| All CTAs link to correct pages and flows | Fidel | July 29 | Pending |
| Personalized result page generates without error for all 20 test scenarios | Fidel | July 29 | Pending |
| Private launch invitee list of 20 approved by Park Dae-hyuk | Ezra + Stacey | July 29 | Pending |
| Launch readiness report drafted and submitted to Park Dae-hyuk | Fidel | July 30 | Pending |

| 07 | Final MVP Acceptance Criteria The 22 conditions that must all be true before private launch |
| --- | --- |

## 7.1  The 22 Acceptance Criteria

The MVP is ready for private launch ONLY when all 22 criteria are confirmed TRUE by their respective owners:

| # | Acceptance Criterion | Confirmed By |
| --- | --- | --- |
| AC-01 | Homepage communicates the core thesis clearly: 'Do not scale inefficient computation.' | Fidel + Jiin |
| AC-02 | Visitor can describe compute bottleneck in non-confidential terms via the Compute Bottleneck Review Surface | Fidel |
| AC-03 | Website responds immediately after submission — no long pause (< 3 seconds) | Fidel |
| AC-04 | Visitor can complete all 9 qualification questions without errors or confusion | Naomi |
| AC-05 | System routes visitor to ALPHA Compute, ALPHA Core, or Both correctly | Fidel + Benjamin |
| AC-06 | System recommends Non-Exclusive, Exclusive, or Strategic pathway correctly | Fidel |
| AC-07 | Personalized ALPHA result page is generated with all 9 sections present | Fidel + Naomi |
| AC-08 | Lead score (0–100) is calculated and lead tier (1–4) is assigned correctly | Fidel |
| AC-09 | CRM record is created automatically for every submission | Naomi |
| AC-10 | Human follow-up owner is assigned automatically in the dashboard | Naomi + Stacey |
| AC-11 | Tier 1 response SLA (24 hours) and Tier 2 SLA (48 hours) are operationally enforced | Naomi + Stacey |
| AC-12 | NDA warning appears on all 5 required surfaces before sensitive detail collection | Fidel |
| AC-13 | Paid evaluation packages (3 types) are clearly defined and accessible | Naomi |
| AC-14 | Exclusive pathway requires executive approval checklist before any exclusivity offer | Fidel |
| AC-15 | All technical claims in AI responses are grounded in Knowledge Core — no hallucinated benchmarks | Benjamin |
| AC-16 | Prohibited language ('lookup-table execution') never appears in any AI response | Benjamin |
| AC-17 | No visible concierge character, avatar, robot, or popup chatbot appears anywhere on the site | Yein + Fidel |
| AC-18 | The experience feels premium, scientific, strategic, minimal, and trustworthy (design QA passed) | Yein |
| AC-19 | All 20 test scenarios documented with PASS or FAIL status — minimum 18/20 PASS | Ezra + Fidel |
| AC-20 | Knowledge Core v1 is complete with approved/prohibited answer database operational | Benjamin |
| AC-21 | Private launch invitee list of 20 strategic visitors approved by Park Dae-hyuk | Ezra + Stacey |
| AC-22 | IWL team can begin operating the online sales channel independently with this document and the Master Architecture document as their guide | Fidel + Park Dae-hyuk |

| LAUNCH GATE | Fidel submits the Launch Readiness Report by July 30. Park Dae-hyuk and CEO Kang approve private launch by July 31. No launch without both approvals. |
| --- | --- |

| 08 | Private Launch Plan How the MVP is tested with 20 selected strategic visitors |
| --- | --- |

## 8.1  Launch Type

Private MVP launch only. The website must not be broadly promoted until the conversion flow is tested with 20 hand-selected strategic visitors. Public launch is out of scope for July.

## 8.2  Private Launch Targets

| Metric | Target | Owner |
| --- | --- | --- |
| Strategic visitors invited | 20 | Ezra (list) + Park Dae-hyuk (approval) |
| Completed ALPHA assessments | 10 | AI Sales Engine |
| Human concierge meetings booked | 5 | Naomi + iTrix team |
| NDA discussions initiated | 2 | Park Dae-hyuk / iTrix |
| Paid evaluation candidates identified | 1 | Fidel + Park Dae-hyuk |
| Strategic feedback interviews conducted | 5 | Naomi + Ezra |

## 8.3  Target Invitee Categories

- Semiconductor executives (CPU, GPU, NPU, AI chip companies)

- Hyperscaler / cloud infrastructure contacts

- HPC / CAE business leaders (simulation, CFD, EDA companies)

- AI infrastructure platform executives (compiler, runtime, deployment companies)

- Energy-aware infrastructure leaders (data center, sovereign AI)

- Strategic investors (corporate VC, sovereign fund, family office)

- Selected technical validators / researchers (for credibility testing)

## 8.4  Private Launch Feedback Collection

For each of the 20 private launch visitors, Ezra and Naomi must document:

- Which prompt or pressure signal card they selected

- What they typed in the open prompt field

- Which product route the system assigned them

- Whether they completed the qualification questions

- Whether they viewed the personalized result page

- Which CTA they clicked

- Whether they provided their email

- Their qualitative feedback on the experience (if available)

- Whether they became a Tier 1 or Tier 2 lead

| FEEDBACK PURPOSE | Private launch feedback becomes the primary input for Knowledge Core improvements, routing logic refinements, and the Stage 2 automation roadmap. Every visitor interaction is market data. |
| --- | --- |

| 09 | Post-Launch: Online Sales Channel Operating Manual How IWL runs the iTrix online sales channel from August onward |
| --- | --- |

## 9.1  IWL's Operating Role from August 2026

After July 31, IWL Partners transitions from builder to operator. This section defines how IWL runs the online sales channel on behalf of iTrix. This is the day-to-day operating manual.

| ROLE BOUNDARY | IWL operates the online sales channel. iTrix retains final authority over technology claims, pricing, contracts, license terms, disclosure boundaries, and legal commitments. IWL cannot independently sign contracts, confirm final pricing, promise technical performance, or grant licenses. |
| --- | --- |

## 9.2  Daily Operating Routine

| Time | Task | Owner | Tool |
| --- | --- | --- | --- |
| Morning (9:00 AM) | Review overnight dashboard for new submissions. Identify any Tier 1 leads requiring same-day response. | Naomi / Stacey | Airtable CRM dashboard |
| Morning (9:30 AM) | For each new Tier 1 lead: review AI-generated summary, confirm product route and license path, draft personalized follow-up email. | Naomi | Dashboard + email draft |
| By 11:00 AM | Send follow-up emails to all new Tier 1 leads. Response must reach visitor within 24 hours of submission. | Naomi | Email (Resend/SendGrid) |
| Midday | Process Tier 2 leads: review summaries, send personalized summary + one clarifying question, offer discovery call. | Naomi | Dashboard + email |
| Afternoon | Update CRM status for all active leads. Record meeting outcomes, open action items, and next steps. | Naomi / Stacey | Airtable CRM |
| End of Day | Escalate to Fidel: any leads requiring technical review, any exclusive/strategic requests, any sensitive disclosure questions. | Naomi | Internal messaging |
| Weekly (Friday) | Prepare weekly pipeline report for Park Dae-hyuk: new leads, meetings booked, NDA discussions, paid evaluation candidates. | Stacey | Dashboard export |

## 9.3  Lead Management Operating Rules

- Every submission gets a CRM record — no exceptions

- Tier 1 response within 24 hours — tracked and reported in weekly dashboard

- Tier 2 response within 48 hours — tracked and reported in weekly dashboard

- Tier 3 automated brief sent within 24 hours — no human follow-up unless visitor re-engages

- Tier 4 educational content only — no human time invested

- Every human interaction is logged in CRM notes

- Status must be updated after every touchpoint: New → Contacted → Meeting Booked → NDA → Evaluation → PoC → Licensed → Closed

- Exclusive / strategic requests escalated to Park Dae-hyuk immediately — never handled by Naomi alone

- Any visitor asking for technical details beyond public level must be flagged for Benjamin's review

## 9.4  Human Concierge Escalation Rules

| Situation | Escalate To | Response Time |
| --- | --- | --- |
| Visitor asks for NDA-only technical details before NDA is signed | Benjamin (technical gate) + Fidel | Within 4 hours |
| Visitor requests exclusive field rights | Park Dae-hyuk + CEO Kang (executive approval required) | Within 24 hours |
| Visitor is a strategic investor or acquirer | Park Dae-hyuk immediately | Within 4 hours |
| Visitor is a government or national AI infrastructure body | Park Dae-hyuk | Within 24 hours |
| AI response appears to have overclaimed or misstated technical information | Benjamin immediately | Within 2 hours |
| Lead score is Tier 1 and visitor represents a semiconductor company or major hyperscaler | Park Dae-hyuk + Fidel | Within 4 hours |
| Visitor requests pricing or contract terms | iTrix CEO Kang (via Park Dae-hyuk) | Within 24 hours |
| Any media inquiry or content creator request | Designated iTrix media contact via Park Dae-hyuk | Within 48 hours |

## 9.5  Monthly Performance Reporting

Stacey prepares a monthly performance report by the 5th of each month for Park Dae-hyuk and CEO Kang. The report covers:

| Report Section | Metrics Included |
| --- | --- |
| Funnel Summary | Total visitors, prompt submissions, email captures, personalized pages generated |
| Lead Quality | Lead score distribution, Tier 1/2/3/4 breakdown, product route distribution (Compute vs Core vs Both) |
| Conversion Performance | Prompt → email capture rate, Tier 1/2 rate among serious visitors, meeting conversion from Tier 1 |
| Pipeline Status | Active NDAs, paid evaluations in progress, PoC negotiations, license discussions |
| Response Time Compliance | Tier 1 average response time, Tier 2 average response time, SLA breaches |
| Knowledge Core Health | Common questions not answered well, prohibited language violations, escalation frequency |
| Top Visitor Insights | Most common bottleneck descriptions, most common industries, most common CTAs clicked |
| Action Items for Next Month | Knowledge Core updates needed, routing logic improvements, content additions |

## 9.6  Content Maintenance Schedule

| Cadence | Task | Owner |
| --- | --- | --- |
| Weekly | Review AI responses from the past week for accuracy, tone, and claim compliance | Benjamin |
| Weekly | Update FAQ database with new questions that came in from visitors | Benjamin + Naomi |
| Bi-weekly | Review and improve content blocks that are getting low engagement | Naomi + Jiin |
| Monthly | Add new use case examples based on real visitor bottleneck descriptions | Ezra + Benjamin |
| Monthly | Review and update prohibited claims list based on iTrix technical team feedback | Benjamin |
| Monthly | Review lead scoring weights against real conversion data and adjust | Fidel |
| Quarterly | Full Knowledge Core audit — all chunks re-reviewed for accuracy and disclosure level | Benjamin + iTrix |
| As needed | Re-ingest updated source documents (new white papers, new arXiv submissions, updated one-pagers) | Fidel + Benjamin |

| 10 | Automation Roadmap — Stage 2 & Stage 3 How the concierge-assisted MVP evolves into a fully automated platform |
| --- | --- |

## 10.1  The Three-Stage Evolution

The concierge model is designed to evolve. Do not automate before learning. Use Stage 1 operations to discover what should be automated, then build it in Stages 2 and 3.

| Stage | Name | Timing | Description | Key Trigger |
| --- | --- | --- | --- | --- |
| Stage 1 | Manual Concierge with AI Assistance | July–October 2026 (MVP) | AI captures and routes. IWL/iTrix manually refines responses, approves sensitive content, and delivers personalized briefings. Humans drive all trust and negotiation. | MVP launch — currently in build |
| Stage 2 | Semi-Automated Concierge | Q4 2026 – Q1 2027 | Repeated questions, customer segments, briefing formats, PoC templates, and follow-up workflows converted into structured AI-assisted modules. Humans still handle exceptions, trust, and deal-closing. | After 50+ visitor interactions documented with consistent patterns |
| Stage 3 | Automated AI Sales Engine | Q2 2027+ | Most repeatable parts of the journey fully automated. AI handles explanation, qualification, follow-up, and preparation end-to-end. Humans focus exclusively on trust, negotiation, legal review, and strategic closing. | After Stage 2 modules validated with real conversion data |

## 10.2  What Gets Automated in Stage 2

- Personalized briefing generation — template-based modules with AI assembly

- Follow-up email sequences — triggered by lead tier and CRM status

- FAQ responses for the 20 most common questions

- Compute Bottleneck Review report generation

- PoC proposal template generation (scope + KPIs)

- Meeting agenda generation

- Lead nurture content delivery for Tier 3

- Weekly pipeline report generation

## 10.3  What Stays Human in Stage 3

- First confidential meeting with Tier 1 leads

- NDA review and signing process

- Paid evaluation scope negotiation

- Exclusive pathway discussions

- Strategic investor and acquirer conversations

- Technical claim approvals and new proof disclosures

- Final commercial term negotiation

- Legal document review

- Partner relationship management

| 11 | Execution Risk Register Risks that threaten the June 30 and July 31 deadlines |
| --- | --- |

## 11.1  Execution Risk Register

| Risk | Severity | Probability | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| iTrix delays providing approved technical materials (AXIOM/CRE/FQNM descriptions) | Critical | Medium | Benjamin escalates to Park Dae-hyuk within 48 hours of missed response. Use public arXiv/thesis for FQNM while awaiting approval for others. | Benjamin + Stacey |
| Brand strategy keeps changing after Week 1 lock | High | Low | Lock positioning in Week 1. Any reopening requires CEO Kang + Park Dae-hyuk joint approval. No changes without formal decision log entry. | Park Dae-hyuk + Stacey |
| Knowledge Core not ready by July 7 | Critical | Medium | Begin Phase 1 (public documents) ingestion immediately in parallel. July 7 deadline is a hard blocker for Sprints 3-6. | Benjamin + Fidel |
| Website feels like a generic chatbot or brochure | High | Low | Compute Bottleneck Review Surface above the fold. No popup chat bubble. No visible concierge. Yein QA before any visitor sees the site. | Yein + Fidel |
| AI overclaims and creates IP or reputational risk | Critical | Medium | RAG architecture limits responses to Knowledge Core. Benjamin owns prohibited claims enforcement. Human review gate for Tier 1/2. | Benjamin |
| Too much scope creep into July build | High | High | Fidel has authority to cut scope. MVP is what's needed for IWL to begin sales operation — not a complete enterprise system. Postpone advanced automation. | Fidel |
| External designer or web developer causes delay | High | Medium | Yein has a 48-hour escalation rule if designer misses deadline. Web developer scope is fixed. Yein + Stacey track weekly. | Yein + Stacey |
| Human follow-up too slow after launch | High | Medium | 24h SLA for Tier 1, 48h for Tier 2. Dashboard alerts for overdue leads. Stacey tracks weekly compliance. | Naomi + Stacey |
| Feedback not consolidated — scattered across platforms | Medium | High | Stacey enforces one-document feedback rule. No feedback is valid unless it goes through Stacey's consolidation document. | Stacey |
| Exclusive rights casually offered to any partner | Critical | Low | Non-exclusive is default. Exclusive requires full approval checklist + CEO Kang + Park Dae-hyuk. System prompt never mentions exclusivity pricing. | Fidel + Park Dae-hyuk |

| 12 | Appendices Supporting reference materials |
| --- | --- |

## Appendix A — Master Deliverables Checklist

Complete list of all deliverables across both workstreams:

### Rebranding Deliverables (Due June 30)

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Final brand positioning (English + Korean) | Jiin | June 30 | Pending |
| Master Message Document | Jiin | June 30 | Pending |
| Alpha Compute one-pager | Jiin | June 30 | Pending |
| Alpha Core one-pager | Jiin | June 30 | Pending |
| Company profile deck | Jiin | June 30 | Pending |
| Strategic partner / investor pitch deck | Jiin | June 30 | Pending |
| Logo package (all formats) | Yein | June 30 | Pending |
| Color and typography system | Yein | June 30 | Pending |
| Visual identity package (name card, signature, letterhead, cover) | Yein | June 30 | Pending |
| Brand guideline document | Yein | June 30 | Pending |
| Homepage version 1.0 | Yein + web dev | June 30 | Pending |
| Message Package for AI Sales Engine handoff | Jiin | June 30 | Pending |

### AI Sales Engine Deliverables (Due July 31)

| Deliverable / Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Knowledge Core v1 (5 namespaces, full metadata, ingested) | Benjamin + Fidel | July 7 | Pending |
| Approved/prohibited answer database | Benjamin | July 7 | Pending |
| AI concierge script v1 (opening, questions, routing, result page) | Fidel + Naomi | July 10 | Pending |
| Product routing and license pathway routing logic | Fidel | July 10 | Pending |
| Lead scoring formula and tier thresholds | Fidel | July 10 | Pending |
| Personalized result page (9 sections, all content blocks) | Fidel + Naomi | July 10 | Pending |
| CRM structure and dashboard (Airtable) | Naomi + Fidel | July 14 | Pending |
| Follow-up email templates (all tiers) | Naomi | July 14 | Pending |
| Offline handoff memo template | Naomi | July 14 | Pending |
| Paid evaluation proposal templates (3 packages) | Naomi | July 21 | Pending |
| PoC proposal template | Naomi | July 21 | Pending |
| NDA checklist | Naomi | July 21 | Pending |
| Contract support draft templates (MOU, LOI, Term Sheet outline) | Naomi | July 21 | Pending |
| Success Team operating checklist | Naomi | July 21 | Pending |
| 20 QA test scenarios documented and passed | Ezra + Fidel | July 29 | Pending |
| Monthly operating dashboard | Stacey | July 29 | Pending |
| Online Sales Operation Manual (this document) | Fidel | July 29 | Pending |
| Private launch invitee list (20) approved by Park Dae-hyuk | Ezra + Stacey | July 29 | Pending |
| Launch readiness report signed off | Fidel | July 30 | Pending |
| Private MVP launch approved by Park Dae-hyuk + CEO Kang | Park Dae-hyuk | July 31 | Pending |

## Appendix B — Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| v1.0 | June 2026 | Fidel Omondi Otieno | Initial release covering complete execution plan, June workstreams, July 10-day sprint, 6 development sprints, Knowledge Core spec, 20 test scenarios, 22 acceptance criteria, private launch plan, post-launch operating manual, and automation roadmap. |

itriX AI Sales Engine — MVP Execution, Milestone & Operations Command

Prepared by Fidel Omondi Otieno for IWL Partners | June 2026 | CONFIDENTIAL

Build it right. Launch it sharp. Operate it well.